## Text
CougSat-1 |  |  |  | V1.4.0 |  |  |  |  | End: | 2020-06-30
Subsystem | Component | Type | Start | Design |  | Implement Part 1 |  | Implement Part 2 |  | Test
Self-contained system within the satellite | Subassembly of the subsystem | Primary discipline | Component commencing | Outlining, prototyping, planning, diagraming, etc. |  | Schematic, mCAD, front end, interfacing, etc. |  | Board layout, machining, backend, assembly, etc. |  | Functional, performance, validation, etc.
| CougSat-1 Flight Unit | Assembly | 2020-03-29 | 2 | 2020-04-12 | 2 | 2020-04-26 | 1 | 2020-05-03 | 6 | 2020-06-14
EPS | Mainboard V2.3 | Hardware | 2020-03-15 | 1 | 2020-03-22 | 1 | 2020-03-29 | 4 | 2020-04-26 | 1 | 2020-05-03
| Solar Panel V2.1 | Hardware | 2018-08-01 | 2 | 2018-08-15 | 74 | 2020-01-15 | 2.5714 | 2020-02-02 | 8 | 2020-03-29
| PMIC | Software | 2018-10-24 | 3 | 2018-11-14 | 71.5714 | 2020-03-29 | 6 | 2020-05-10 | 4 | 2020-06-07
Avionics | Mainboard V1.1 | Hardware | 2018-10-31 | 3 | 2018-11-21 | 43 | 2019-09-18 | 19.5714 | 2020-02-02 | 6 | 2020-03-15
| ADCS Controller | Software | 2018-09-26 | 58 | 2019-11-06 | 16 | 2020-02-26 | 8.5714 | 2020-04-26 | 6 | 2020-06-07
| IFJR Controller | Software | 2019-04-03 | 31 | 2019-11-06 | 16 | 2020-02-26 | 6.5714 | 2020-04-12 | 4 | 2020-05-10
| IHU | Software | 2018-09-26 | 58 | 2019-11-06 | 16 | 2020-02-26 | 10.5714 | 2020-05-10 | 4 | 2020-06-07
Communications | Comms PCB V1.2 | Hardware | 2019-10-23 | 2 | 2019-11-06 | 2 | 2019-11-20 | 10.5714 | 2020-02-02 | 4 | 2020-03-01
| Comms Controller | Software | 2019-02-06 | 31 | 2019-09-11 | 26 | 2020-03-11 | 6.5714 | 2020-04-26 | 6 | 2020-06-07
| +X Panel V1.0 | Hardware | 2018-09-26 | 4 | 2018-10-24 | 23 | 2019-04-03 | 35 | 2019-12-04 | 8.5714 | 2020-02-02
| -Z Panel V1.0 | Hardware | 2018-10-31 | 4 | 2018-11-28 | 43 | 2019-09-25 | 18.5714 | 2020-02-02 | 6 | 2020-03-15
| Ground Station V1.0 | Hardware | 2018-08-29 | 8 | 2018-10-24 | 4 | 2018-11-21 | 66.5714 | 2020-03-01 | 2 | 2020-03-15
| Ground Computer | Software | 2018-05-23 | 68 | 2019-09-11 | 16 | 2020-01-01 | 12 | 2020-03-25 | 6 | 2020-05-06
Payload | Camera PCB V1.1 | Hardware | 2018-10-24 | 44 | 2019-08-28 | 4 | 2019-09-25 | 8 | 2019-11-20 | 10.5714 | 2020-02-02
| Germination PCB V1.0 | Hardware | 2018-10-24 | 46 | 2019-09-11 | 20.5714 | 2020-02-02 | 6 | 2020-03-15 | 6 | 2020-04-26
Mechanical | Structure V1.1 | Hardware | 2020-02-16 | 2 | 2020-03-01 | 2 | 2020-03-15 | 4 | 2020-04-12 | 2 | 2020-04-26
| Germination | Hardware | 2018-05-23 | 7 | 2018-07-11 | 85.5714 | 2020-03-01 | 4 | 2020-03-29 | 4 | 2020-04-26
Milestones
Name |  | Description | [8 empty] | Date
FU Integration |  | Assembly of all flight ready subsystems and components | [8 empty] | 2020-04-26
FU Day in the Life Test |  | A duration test of the flight unit in simulated space environment | [8 empty] | 2020-05-03
FRR |  | Review of the flight unit to determine its readiness to fly | [8 empty] | 2020-06-21
MRR |  | Review of the mission to determine its readiness to execute | [8 empty] | 2020-06-28
ILC |  | Initial launch capabilities | [8 empty] | 2020-06-30
Formulas:
Date = [Date, row above]+7

## Gantt Lines (hidden)
| Today: 26-Jan-20 | 2020-01-05 | 43835 | 43863
2020-01-26 | 0
2020-01-26 | 1
FU Integration
2020-04-26 | 0
2020-04-26 | 1
FU Day in the Life Test
2020-05-03 | 0
2020-05-03 | 1
FRR
2020-06-21 | 0
2020-06-21 | 1
MRR
2020-06-28 | 0
2020-06-28 | 1
ILC
2020-06-30 | 0
2020-06-30 | 1