## Text
CougSat-1 |  |  |  |  | V1.5.1 |  |  | End: | 2020-06-28
Milestone | Component | Type | Critical Path | Start | Build |  | Test |  | Margin
Collection of tasks that mark important dates | Subsystem assembly | Primary discipline | Last component of the milestone | Component commencing | Design, implement, fabricate, assemble, etc. |  | Functional, performance, validation, etc. |  | Excess buffer for the unexpected
CougSat-1 Flight Unit | CougSat-1 Flight Unit | Assembly |  | 2019-05-01 | 52.5714 | 2020-05-03 | 2 | 2020-05-17 | 3 | 2020-06-07
| EPS V3.1 | Hardware | Critical Path | 2020-02-16 | 7 | 2020-04-05 | 2 | 2020-04-19 | 2 | 2020-05-03
| Structure V1.1 | Hardware |  | 2020-03-01 | 4 | 2020-03-29 | 2 | 2020-04-12 | 2 | 2020-04-26
| Avionics V1.1 | Hardware |  | 2019-05-01 | 44.5714 | 2020-03-08 | 4 | 2020-04-05 | 2 | 2020-04-19
| Solar Panel V2.1 | Hardware |  | 2019-09-03 | 26.7143 | 2020-03-08 | 2 | 2020-03-22 | 2 | 2020-04-05
| +X Panel V1.1 | Hardware |  | 2020-02-16 | 4 | 2020-03-15 | 1 | 2020-03-22 | 2 | 2020-04-05
| Comms V1.1 | Hardware |  | 2020-01-01 | 6.5714 | 2020-02-16 | 4 | 2020-03-15 | 2 | 2020-03-29
| Backplane V3.2 | Hardware |  | 2020-02-02 | 5 | 2020-03-08 | 1 | 2020-03-15 | 2 | 2020-03-29
| -Z Panel V1.0 | Hardware |  | 2019-05-01 | 44.5714 | 2020-03-08 | 1 | 2020-03-15 | 2 | 2020-03-29
| Germination Chamber | Hardware |  | 2019-05-01 | 47.5714 | 2020-03-29 | 2 | 2020-04-12 | 2 | 2020-04-26
| Germination Board V1.0 | Hardware |  | 2019-09-25 | 24.5714 | 2020-03-15 | 2 | 2020-03-29 | 2 | 2020-04-12
| Camera Board V1.1 | Hardware |  | 2019-09-11 | 9.5714 | 2019-11-17 | 13 | 2020-02-16 | 2 | 2020-03-01
Software Test | Day in the Life Test | Software |  | 2020-05-03 | 4 | 2020-05-31 | 1 | 2020-06-07 | 3 | 2020-06-28
| IHU - C&DH Controller | Software | Critical Path | 2019-05-01 | 50.5714 | 2020-04-19 | 4 | 2020-05-17 | 2 | 2020-05-31
| ADCS Controller | Software | Critical Path | 2019-05-01 | 48.5714 | 2020-04-05 | 6 | 2020-05-17 | 2 | 2020-05-31
| Comms Controller | Software | Critical Path | 2019-05-01 | 48.5714 | 2020-04-05 | 6 | 2020-05-17 | 2 | 2020-05-31
| IFJR | Software |  | 2019-05-01 | 49.5714 | 2020-04-12 | 4 | 2020-05-10 | 2 | 2020-05-24
| PMIC - EPS Controller | Software |  | 2019-05-01 | 48.5714 | 2020-04-05 | 4 | 2020-05-03 | 2 | 2020-05-17
Important Dates
Name |  | Description | [7 empty] | Date
Radio Licensing Forms |  | All RF regulatory documents completed and being processed by regulatory bodies (FCC) | [7 empty] | 2020-03-01
Battery Qualification |  | Testing the batteries per the testing plan | [7 empty] | 2020-03-08
Flight Unit Integration |  | All flight ready hardware assembled, wiring harnesses installed | [7 empty] | 2020-05-03
Vibration Test |  | Mechanical test to ensure launch surviability, only critical hardware fixes will be installed | [7 empty] | 2020-05-10
Software Integration |  | All flight ready software installed, only critical bug fixes will be installed | [7 empty] | 2020-05-31
Day in the Life Test |  | A duration test of the flight unit in simulated space environment | [7 empty] | 2020-06-07
Nanoracks Handover |  | Delivery to launch provider | [7 empty] | 2020-06-28

## Gantt Lines
| Today: 14-Feb-20 | 2020-02-02 | 43863 | 43891
2020-02-14 | 0
2020-02-14 | 1
Radio Licensing Forms
2020-03-01 | 0
2020-03-01 | 1
Battery Qualification
2020-03-08 | 0
2020-03-08 | 1
Flight Unit Integration
2020-05-03 | 0
2020-05-03 | 1
Vibration Test
2020-05-10 | 0
2020-05-10 | 1
Software Integration
2020-05-31 | 0
2020-05-31 | 1
Day in the Life Test
2020-06-07 | 0
2020-06-07 | 1
Nanoracks Handover
2020-06-28 | 0
2020-06-28 | 1