## Text
CougSat-1 |  |  |  |  | V1.5.1 |  |  | End: | 2021-01-18
Milestone | Component | Type | Critical Path | Start | Build |  | Test |  | Margin
Collection of tasks that mark important dates | Subsystem assembly | Primary discipline | Last component of the milestone | Component commencing | Design, implement, fabricate, assemble, etc. |  | Functional, performance, validation, etc. |  | Excess buffer for the unexpected
CougSat-1 Flight Unit | CougSat-1 Flight Unit | Assembly |  | 2020-08-24 | 14 | 2020-11-30 | 2 | 2020-12-14 | 3 | 2021-01-04
| EPS V3.1 | Hardware |  | 2020-08-24 | 4 | 2020-09-21 | 4 | 2020-10-19 | 2 | 2020-11-02
| Battery Testing | Hardware |  | 2020-08-24 | 2 | 2020-09-07 | 4 | 2020-10-05 | 2 | 2020-10-19
| Structure V1.1 | Hardware |  | 2020-08-24 | 4 | 2020-09-21 | 4 | 2020-10-19 | 2 | 2020-11-02
| Avionics V1.1 | Hardware | Critical Path | 2020-08-24 | 8 | 2020-10-19 | 4 | 2020-11-16 | 2 | 2020-11-30
| Solar Panel V2.1 | Hardware |  | 2020-08-24 | 4 | 2020-09-21 | 2 | 2020-10-05 | 2 | 2020-10-19
| +X Panel V1.1 | Hardware |  | 2020-08-24 | 8 | 2020-10-19 | 2 | 2020-11-02 | 2 | 2020-11-16
| Comms V1.1 | Hardware |  | 2020-08-24 | 4 | 2020-09-21 | 6 | 2020-11-02 | 2 | 2020-11-16
| Backplane V3.2 | Hardware |  | 2020-08-24 | 2 | 2020-09-07 | 2 | 2020-09-21 | 2 | 2020-10-05
| -Z Panel V1.0 | Hardware |  | 2020-08-24 | 4 | 2020-09-21 | 2 | 2020-10-05 | 2 | 2020-10-19
| Germination Chamber | Hardware |  | 2020-08-24 | 6 | 2020-10-05 | 4 | 2020-11-02 | 2 | 2020-11-16
| Germination Board V1.0 | Hardware |  | 2020-08-24 | 8 | 2020-10-19 | 2 | 2020-11-02 | 2 | 2020-11-16
| Camera Board V1.1 | Hardware |  | 2020-08-24 | 4 | 2020-09-21 | 2 | 2020-10-05 | 2 | 2020-10-19
Software Test | Day in the Life Test | Software |  | 2020-08-24 | 16 | 2020-12-14 | 3 | 2021-01-04 | 2 | 2021-01-18
| IHU - C&DH Controller | Software | Critical Path | 2020-08-24 | 10 | 2020-11-02 | 4 | 2020-11-30 | 2 | 2020-12-14
| ADCS Controller | Software | Critical Path | 2020-08-24 | 10 | 2020-11-02 | 4 | 2020-11-30 | 2 | 2020-12-14
| Comms Controller | Software | Critical Path | 2020-08-24 | 10 | 2020-11-02 | 4 | 2020-11-30 | 2 | 2020-12-14
| IFJR | Software | Critical Path | 2020-08-24 | 10 | 2020-11-02 | 4 | 2020-11-30 | 2 | 2020-12-14
| PMIC - EPS Controller | Software | Critical Path | 2020-08-24 | 10 | 2020-11-02 | 4 | 2020-11-30 | 2 | 2020-12-14
Important Dates
Name |  | Description | [7 empty] | Date
Radio Licensing Forms |  | All RF regulatory documents completed and being processed by regulatory bodies (FCC) | [7 empty] | 2020-03-01
Battery Qualification |  | Testing the batteries per the testing plan | [7 empty] | 2020-03-08
Flight Unit Integration |  | All flight ready hardware assembled, wiring harnesses installed | [7 empty] | 2020-11-30
Vibration Test |  | Mechanical test to ensure launch surviability, only critical hardware fixes will be installed | [7 empty] | 2020-12-07
Software Integration |  | All flight ready software installed, only critical bug fixes will be installed | [7 empty] | 2020-12-14
Day in the Life Test |  | A duration test of the flight unit in simulated space environment | [7 empty] | 2021-01-04
Nanoracks Handover |  | Delivery to launch provider | [7 empty] | 2021-01-18

## Gantt Lines
| Today: 19-Aug-20 | 2020-08-23 | 44066 | 44094
2020-08-19 | 0
2020-08-19 | 1
Radio Licensing Forms
2020-03-01 | 0
2020-03-01 | 1
Battery Qualification
2020-03-08 | 0
2020-03-08 | 1
Flight Unit Integration
2020-11-30 | 0
2020-11-30 | 1
Vibration Test
2020-12-07 | 0
2020-12-07 | 1
Software Integration
2020-12-14 | 0
2020-12-14 | 1
Day in the Life Test
2021-01-04 | 0
2021-01-04 | 1
Nanoracks Handover
2021-01-18 | 0
2021-01-18 | 1