## Text
CougSat-1 |  |  |  | V1.2.1 |  |  |  |  | End: | 2020-05-27
Subsystem | Component | Type | Start | Design |  | Implement Part 1 |  | Implement Part 2 |  | Test
Self-contained system within the satellite | Subassembly of the subsystem | Primary discipline | Component commencing | Outlining, prototyping, planning, diagraming, etc. |  | Schematic, mCAD, front end, interfacing, etc. |  | Board layout, machining, backend, assembly, etc. |  | Functional, performance, validation, etc.
CougSat-1 | Engineering Model | Assembly | 2018-05-02 | 3 | 2018-05-23 | 82 | 2019-12-18 | 1 | 2019-12-25 | 5 | 2020-01-29
| Flight Unit | Assembly | 2019-12-25 | 4 | 2020-01-22 | 4 | 2020-02-19 | 8 | 2020-04-15 | 12 | 2020-05-27
EPS | Mainboard V2.1 | Hardware | 2018-05-23 | 2 | 2018-06-06 | 8 | 2018-08-01 | 18 | 2018-12-05 | 17 | 2019-04-03
| Mainboard V2.2 | Hardware | 2018-12-05 | 17 | 2019-04-03 | 2 | 2019-04-17 | 6 | 2019-05-29 | 4 | 2019-06-26
| Solar Panel | Hardware | 2018-08-01 | 2 | 2018-08-15 | 8 | 2018-10-10 | 26 | 2019-04-10 | 8 | 2019-06-05
| Backplane V2.0 | Hardware | 2018-08-29 | 2 | 2018-09-12 | 3 | 2018-10-03 | 10 | 2018-12-12 | 11 | 2019-02-27
| Backplane V3.0 | Hardware | 2018-12-12 | 11 | 2019-02-27 | 2 | 2019-03-13 | 6 | 2019-04-24 | 2 | 2019-05-08
| PMIC | Software | 2018-10-24 | 3 | 2018-11-14 | 20 | 2019-04-03 | 8 | 2019-05-29 | 8 | 2019-07-24
Avionics | Mainboard V1.1 | Hardware | 2018-10-31 | 3 | 2018-11-21 | 19 | 2019-04-03 | 16 | 2019-07-24 | 8 | 2019-09-18
| ADCS Controller | Software | 2018-09-26 | 10 | 2018-12-05 | 17 | 2019-04-03 | 14 | 2019-07-10 | 8 | 2019-09-04
| IFJR Controller | Software | 2019-04-03 | 8 | 2019-05-29 | 8 | 2019-07-24 | 12 | 2019-10-16 | 8 | 2019-12-11
| IHU | Software | 2018-09-26 | 14 | 2019-01-02 | 20 | 2019-05-22 | 8 | 2019-07-17 | 8 | 2019-09-11
Communications | Comms PCB V1.0 | Hardware | 2018-08-29 | 11 | 2018-11-14 | 8 | 2019-01-09 | 12 | 2019-04-03 | 8 | 2019-05-29
| Comms PCB V1.1 | Hardware | 2019-04-03 | 8 | 2019-05-29 | 2 | 2019-06-12 | 6 | 2019-07-24 | 4 | 2019-08-21
| Comms Controller | Software | 2019-02-06 | 8 | 2019-04-03 | 4 | 2019-05-01 | 12 | 2019-07-24 | 8 | 2019-09-18
| +X Panel V1.0 | Hardware | 2018-09-26 | 3 | 2018-10-17 | 24 | 2019-04-03 | 6 | 2019-05-15 | 6 | 2019-06-26
| -Z Panel V1.0 | Hardware | 2018-10-31 | 1 | 2018-11-07 | 21 | 2019-04-03 | 6 | 2019-05-15 | 6 | 2019-06-26
| Ground Station V1.0 | Hardware | 2018-08-29 | 8 | 2018-10-24 | 4 | 2018-11-21 | 22 | 2019-04-24 | 2 | 2019-05-08
| Ground Computer | Software | 2018-05-23 | 3 | 2018-06-13 | 44 | 2019-04-17 | 20 | 2019-09-04 | 8 | 2019-10-30
Payload | Camera PCB V1.1 | Hardware | 2018-10-24 | 26 | 2019-04-24 | 4 | 2019-05-22 | 8 | 2019-07-17 | 4 | 2019-08-14
| Germination PCB V1.0 | Hardware | 2018-10-24 | 44 | 2019-08-28 | 4 | 2019-09-25 | 8 | 2019-11-20 | 4 | 2019-12-18
Mechanical | Structure | Hardware | 2018-05-23 | 3 | 2018-06-13 | 36 | 2019-02-20 | 12 | 2019-05-15 | 8 | 2019-07-10
| Germination | Hardware | 2018-05-23 | 7 | 2018-07-11 | 40 | 2019-04-17 | 12 | 2019-07-10 | 8 | 2019-09-04
Milestones
Name |  | Description | [8 empty] | Date
EM Integration |  | Assembly of all subsystems and components. Requires: all hardware done | [8 empty] | 2019-12-18
EM Day in the Life Test |  | A duration test of the satellite in simulated space environment. Requires: all software done | [8 empty] | 2019-12-25
FU Integration |  | Assembly of all flight ready subsystems and components | [8 empty] | 2020-02-19
FU Day in the Life Test |  | A duration test of the flight unit in simulated space environment | [8 empty] | 2020-04-15
FRR |  | Review of the flight unit to determine its readiness to fly | [8 empty] | 2020-04-29
MRR |  | Review of the mission to determine its readiness to execute | [8 empty] | 2020-05-13
ILC |  | Initial launch capabilities | [8 empty] | 2020-05-27
Formulas:
Date = MAX(L6:L26, [Date, row above] + 7)
Date = [Date, row above]+14

## Gantt Lines
| Today: 07-Apr-19 | 2020-05-27 | 43978
2019-04-07 | 0
2019-04-07 | 1
EM Integration
2019-12-18 | 0
2019-12-18 | 1
EM Day in the Life Test
2019-12-25 | 0
2019-12-25 | 1
FU Integration
2020-02-19 | 0
2020-02-19 | 1
FU Day in the Life Test
2020-04-15 | 0
2020-04-15 | 1
FRR
2020-04-29 | 0
2020-04-29 | 1
MRR
2020-05-13 | 0
2020-05-13 | 1
ILC
2020-05-27 | 0
2020-05-27 | 1