## Text
CougSat-1 |  |  |  |  | V1.5.3 |  |  | End: | 2022-07-14
Milestone | Component | Type | Critical Path | Start | Build |  | Test |  | Margin
Collection of tasks that mark important dates | Subsystem assembly | Primary discipline | Last component of the milestone | Component commencing | Design, implement, fabricate, assemble, etc. |  | Functional, performance, validation, etc. |  | Excess buffer for the unexpected
CougSat-1 Flight Unit | CougSat-1 Flight Unit | Assembly |  | 2021-08-23 | 22 | 2022-01-24 | 20.4286 | 2022-06-16 | 4 | 2022-07-14
| EPS V3.1 | Hardware |  | 2021-08-23 | 4 | 2021-09-20 | 4 | 2021-10-18 | 2 | 2021-11-01
| Battery Testing | Hardware |  | 2021-08-23 | 22 | 2022-01-24 | 20.4286 | 2022-06-16 | 2 | 2022-06-30
| Structure V1.1 | Hardware |  | 2021-08-23 | 4 | 2021-09-20 | 4 | 2021-10-18 | 2 | 2021-11-01
| Avionics V1.1 | Hardware |  | 2021-08-23 | 8 | 2021-10-18 | 4 | 2021-11-15 | 2 | 2021-11-29
| Solar Panel V2.1 | Hardware |  | 2021-08-23 | 4 | 2021-09-20 | 2 | 2021-10-04 | 2 | 2021-10-18
| +X Panel V1.1 | Hardware |  | 2021-08-23 | 8 | 2021-10-18 | 2 | 2021-11-01 | 2 | 2021-11-15
| Comms V1.1 | Hardware |  | 2021-08-23 | 4 | 2021-09-20 | 6 | 2021-11-01 | 2 | 2021-11-15
| Backplane V3.2 | Hardware |  | 2021-08-23 | 2 | 2021-09-06 | 2 | 2021-09-20 | 2 | 2021-10-04
| -Z Panel V1.0 | Hardware |  | 2021-08-23 | 4 | 2021-09-20 | 2 | 2021-10-04 | 2 | 2021-10-18
| Germination Chamber | Hardware |  | 2021-08-23 | 10.8571 | 2021-11-07 | 9 | 2022-01-09 | 2 | 2022-01-23
| Germination Board V1.0 | Hardware |  | 2021-08-23 | 8 | 2021-10-18 | 2 | 2021-11-01 | 2 | 2021-11-15
| Camera Board V1.1 | Hardware |  | 2021-08-23 | 4 | 2021-09-20 | 2 | 2021-10-04 | 2 | 2021-10-18
Software Test | Day in the Life Test | Software |  | 2021-08-23 | 16 | 2021-12-13 | 20.5714 | 2022-05-06 | 2 | 2022-05-20
| IHU - C&DH Controller | Software |  | 2021-08-23 | 16 | 2021-12-13 | 20.5714 | 2022-05-06 | 2 | 2022-05-20
| ADCS Controller | Software |  | 2021-08-23 | 16 | 2021-12-13 | 20.5714 | 2022-05-06 | 2 | 2022-05-20
| Comms Controller | Software |  | 2021-08-23 | 16 | 2021-12-13 | 20.5714 | 2022-05-06 | 2 | 2022-05-20
| IFJR | Software |  | 2021-08-23 | 16 | 2021-12-13 | 20.5714 | 2022-05-06 | 2 | 2022-05-20
| PMIC - EPS Controller | Software |  | 2021-08-23 | 16 | 2021-12-13 | 20.5714 | 2022-05-06 | 2 | 2022-05-20
Important Dates
Name |  | Description | [7 empty] | Date
Radio Licensing Forms |  | All RF regulatory documents completed and being processed by regulatory bodies (FCC) | [7 empty] | 2020-03-01
Battery Qualification |  | Testing the batteries per the testing plan | [7 empty] | 2022-05-30
Flight Unit Integration |  | All flight ready hardware assembled, wiring harnesses installed | [7 empty] | 2022-05-30
Vibration Test |  | Mechanical test to ensure launch surviability, only critical hardware fixes will be installed | [7 empty] | 2022-06-30
Software Integration |  | All flight ready software installed, only critical bug fixes will be installed | [7 empty] | 2022-05-06
Day in the Life Test |  | A duration test of the flight unit in simulated space environment | [7 empty] | 2022-05-06
Nanoracks Handover |  | Delivery to launch provider | [7 empty] | 2022-06-16

## Gantt Lines
| Today: 12-May-22 | 2021-08-23 | 44431 | 44459
2022-05-12 | 0
2022-05-12 | 1
Radio Licensing Forms
2020-03-01 | 0
2020-03-01 | 1
Battery Qualification
2022-05-30 | 0
2022-05-30 | 1
Flight Unit Integration
2022-05-30 | 0
2022-05-30 | 1
Vibration Test
2022-06-30 | 0
2022-06-30 | 1
Software Integration
2022-05-06 | 0
2022-05-06 | 1
Day in the Life Test
2022-05-06 | 0
2022-05-06 | 1
Nanoracks Handover
2022-06-16 | 0
2022-06-16 | 1