## Text
CougSat-1 |  |  |  |  | V1.5.1 |  |  | End: | 2022-01-17
Milestone | Component | Type | Critical Path | Start | Build |  | Test |  | Margin
Collection of tasks that mark important dates | Subsystem assembly | Primary discipline | Last component of the milestone | Component commencing | Design, implement, fabricate, assemble, etc. |  | Functional, performance, validation, etc. |  | Excess buffer for the unexpected
CougSat-1 Flight Unit | CougSat-1 Flight Unit | Assembly |  | 2021-08-23 | 14 | 2021-11-29 | 2 | 2021-12-13 | 3 | 2022-01-03
| EPS V3.1 | Hardware |  | 2021-08-23 | 4 | 2021-09-20 | 4 | 2021-10-18 | 2 | 2021-11-01
| Battery Testing | Hardware |  | 2021-08-23 | 2 | 2021-09-06 | 4 | 2021-10-04 | 2 | 2021-10-18
| Structure V1.1 | Hardware |  | 2021-08-23 | 4 | 2021-09-20 | 4 | 2021-10-18 | 2 | 2021-11-01
| Avionics V1.1 | Hardware | Critical Path | 2021-08-23 | 8 | 2021-10-18 | 4 | 2021-11-15 | 2 | 2021-11-29
| Solar Panel V2.1 | Hardware |  | 2021-08-23 | 4 | 2021-09-20 | 2 | 2021-10-04 | 2 | 2021-10-18
| +X Panel V1.1 | Hardware |  | 2021-08-23 | 8 | 2021-10-18 | 2 | 2021-11-01 | 2 | 2021-11-15
| Comms V1.1 | Hardware |  | 2021-08-23 | 4 | 2021-09-20 | 6 | 2021-11-01 | 2 | 2021-11-15
| Backplane V3.2 | Hardware |  | 2021-08-23 | 2 | 2021-09-06 | 2 | 2021-09-20 | 2 | 2021-10-04
| -Z Panel V1.0 | Hardware |  | 2021-08-23 | 4 | 2021-09-20 | 2 | 2021-10-04 | 2 | 2021-10-18
| Germination Chamber | Hardware |  | 2021-08-23 | 6 | 2021-10-04 | 4 | 2021-11-01 | 2 | 2021-11-15
| Germination Board V1.0 | Hardware |  | 2021-08-23 | 8 | 2021-10-18 | 2 | 2021-11-01 | 2 | 2021-11-15
| Camera Board V1.1 | Hardware |  | 2021-08-23 | 4 | 2021-09-20 | 2 | 2021-10-04 | 2 | 2021-10-18
Software Test | Day in the Life Test | Software |  | 2021-08-23 | 16 | 2021-12-13 | 3 | 2022-01-03 | 2 | 2022-01-17
| IHU - C&DH Controller | Software | Critical Path | 2021-08-23 | 10 | 2021-11-01 | 4 | 2021-11-29 | 2 | 2021-12-13
| ADCS Controller | Software | Critical Path | 2021-08-23 | 10 | 2021-11-01 | 4 | 2021-11-29 | 2 | 2021-12-13
| Comms Controller | Software | Critical Path | 2021-08-23 | 10 | 2021-11-01 | 4 | 2021-11-29 | 2 | 2021-12-13
| IFJR | Software | Critical Path | 2021-08-23 | 10 | 2021-11-01 | 4 | 2021-11-29 | 2 | 2021-12-13
| PMIC - EPS Controller | Software | Critical Path | 2021-08-23 | 10 | 2021-11-01 | 4 | 2021-11-29 | 2 | 2021-12-13
Important Dates
Name |  | Description | [7 empty] | Date
Radio Licensing Forms |  | All RF regulatory documents completed and being processed by regulatory bodies (FCC) | [7 empty] | 2020-03-01
Battery Qualification |  | Testing the batteries per the testing plan | [7 empty] | 2020-03-08
Flight Unit Integration |  | All flight ready hardware assembled, wiring harnesses installed | [7 empty] | 2021-11-29
Vibration Test |  | Mechanical test to ensure launch surviability, only critical hardware fixes will be installed | [7 empty] | 2021-12-06
Software Integration |  | All flight ready software installed, only critical bug fixes will be installed | [7 empty] | 2021-12-13
Day in the Life Test |  | A duration test of the flight unit in simulated space environment | [7 empty] | 2022-01-03
Nanoracks Handover |  | Delivery to launch provider | [7 empty] | 2022-01-17

## Gantt Lines
| Today: 18-Feb-21 | 2021-08-23 | 44431 | 44459
2021-02-18 | 0
2021-02-18 | 1
Radio Licensing Forms
2020-03-01 | 0
2020-03-01 | 1
Battery Qualification
2020-03-08 | 0
2020-03-08 | 1
Flight Unit Integration
2021-11-29 | 0
2021-11-29 | 1
Vibration Test
2021-12-06 | 0
2021-12-06 | 1
Software Integration
2021-12-13 | 0
2021-12-13 | 1
Day in the Life Test
2022-01-03 | 0
2022-01-03 | 1
Nanoracks Handover
2022-01-17 | 0
2022-01-17 | 1