## Text
CougSat-1 |  |  |  | V1.1.0 | Start: | 2018-05-01 |  | 64 | End: | 2019-07-23
Subsystem | Component | Type | Start | Design |  | Implement Part 1 |  | Implement Part 2 |  | Test
Self-contained system within the satellite | Subassembly of the subsystem | Primary discipline | Component commencing | Outlining, prototyping, planning, diagraming, etc. |  | Schematic, mCAD, front end, interfacing, etc. |  | Board layout, machining, backend, assembly, etc. |  | Functional, performance, validation, etc.
CougSat-1 | Engineering Model | Assembly | 2018-05-01 | 3 | 2018-05-22 | 40 | 2019-02-26 | 2 | 2019-03-12 | 4 | 2019-04-09
| Flight Unit | Assembly | 2019-03-12 | 2 | 2019-03-26 | 7 | 2019-05-14 | 2 | 2019-05-28 | 8 | 2019-07-23
EPS | Mainboard | Hardware | 2018-05-22 | 2 | 2018-06-05 | 8 | 2018-07-31 | 11 | 2018-10-16 | 3 | 2018-11-06
| Solar Panel | Hardware | 2018-07-31 | 2 | 2018-08-14 | 8 | 2018-10-09 | 4 | 2018-11-06 | 3 | 2018-11-27
| Backplane | Hardware | 2018-08-28 | 2 | 2018-09-11 | 3 | 2018-10-02 | 3 | 2018-10-23 | 3 | 2018-11-13
| PMIC | Software | 2018-10-23 | 3 | 2018-11-13 | 8 | 2019-01-08 | 3 | 2019-01-29 | 3 | 2019-02-19
Avionics | Mainboard | Hardware | 2018-08-28 | 3 | 2018-09-18 | 7 | 2018-11-06 | 7 | 2018-12-25 | 3 | 2019-01-15
| ADCS Controller | Software | 2018-09-25 | 7 | 2018-11-13 | 7 | 2019-01-01 | 3 | 2019-01-22 | 7 | 2019-03-12
| IFJR Controller | Software | 2018-11-13 | 3 | 2018-12-04 | 7 | 2019-01-22 | 3 | 2019-02-12 | 7 | 2019-04-02
| IHU | Software | 2018-09-25 | 3 | 2018-10-16 | 11 | 2019-01-01 | 3 | 2019-01-22 | 7 | 2019-03-12
Communications | Comms PCB | Hardware | 2018-08-28 | 7 | 2018-10-16 | 8 | 2018-12-11 | 8 | 2019-02-05 | 3 | 2019-02-26
| Comms Controller | Software | 2018-11-13 | 7 | 2019-01-01 | 3 | 2019-01-22 | 6 | 2019-03-05 | 7 | 2019-04-23
| +X Panel | Hardware | 2018-09-25 | 3 | 2018-10-16 | 2 | 2018-10-30 | 2 | 2018-11-13 | 3 | 2018-12-04
| Ground Station | Hardware | 2018-08-28 | 8 | 2018-10-23 | 2 | 2018-11-06 | 1 | 2018-11-13 | 3 | 2018-12-04
| Ground Computer | Software | 2018-05-22 | 3 | 2018-06-12 | 14 | 2018-09-18 | 14 | 2018-12-25 | 7 | 2019-02-12
Payload | Camera PCB | Hardware | 2018-10-23 | 2 | 2018-11-06 | 4 | 2018-12-04 | 4 | 2019-01-01 | 3 | 2019-01-22
| Germination PCB | Hardware | 2018-10-23 | 2 | 2018-11-06 | 4 | 2018-12-04 | 4 | 2019-01-01 | 3 | 2019-01-22
Mechanical | Structure | Hardware | 2018-05-22 | 3 | 2018-06-12 | 14 | 2018-09-18 | 7 | 2018-11-06 | 3 | 2018-11-27
| Germination | Hardware | 2018-05-22 | 7 | 2018-07-10 | 11 | 2018-09-25 | 7 | 2018-11-13 | 8 | 2019-01-08