## Text
CougSat-1 |  |  |  |  | V1.5.1 |  |  | End: | 2020-12-30
Milestone | Component | Type | Critical Path | Start | Build |  | Test |  | Margin
Collection of tasks that mark important dates | Subsystem assembly | Primary discipline | Last component of the milestone | Component commencing | Design, implement, fabricate, assemble, etc. |  | Functional, performance, validation, etc. |  | Excess buffer for the unexpected
CougSat-1 Flight Unit | CougSat-1 Flight Unit | Assembly |  | 2020-08-05 | 14 | 2020-11-11 | 2 | 2020-11-25 | 3 | 2020-12-16
| EPS V3.1 | Hardware |  | 2020-08-05 | 4 | 2020-09-02 | 4 | 2020-09-30 | 2 | 2020-10-14
| Structure V1.1 | Hardware |  | 2020-08-05 | 4 | 2020-09-02 | 4 | 2020-09-30 | 2 | 2020-10-14
| Avionics V1.1 | Hardware | Critical Path | 2020-08-05 | 8 | 2020-09-30 | 4 | 2020-10-28 | 2 | 2020-11-11
| Solar Panel V2.1 | Hardware |  | 2020-08-05 | 4 | 2020-09-02 | 2 | 2020-09-16 | 2 | 2020-09-30
| +X Panel V1.1 | Hardware |  | 2020-08-05 | 8 | 2020-09-30 | 2 | 2020-10-14 | 2 | 2020-10-28
| Comms V1.1 | Hardware |  | 2020-08-05 | 4 | 2020-09-02 | 6 | 2020-10-14 | 2 | 2020-10-28
| Backplane V3.2 | Hardware |  | 2020-08-05 | 2 | 2020-08-19 | 2 | 2020-09-02 | 2 | 2020-09-16
| -Z Panel V1.0 | Hardware |  | 2020-08-05 | 4 | 2020-09-02 | 2 | 2020-09-16 | 2 | 2020-09-30
| Germination Chamber | Hardware |  | 2020-08-05 | 6 | 2020-09-16 | 4 | 2020-10-14 | 2 | 2020-10-28
| Germination Board V1.0 | Hardware |  | 2020-08-05 | 8 | 2020-09-30 | 2 | 2020-10-14 | 2 | 2020-10-28
| Camera Board V1.1 | Hardware |  | 2020-08-05 | 4 | 2020-09-02 | 2 | 2020-09-16 | 2 | 2020-09-30
Software Test | Day in the Life Test | Software |  | 2020-08-05 | 16 | 2020-11-25 | 3 | 2020-12-16 | 2 | 2020-12-30
| IHU - C&DH Controller | Software | Critical Path | 2020-08-05 | 10 | 2020-10-14 | 4 | 2020-11-11 | 2 | 2020-11-25
| ADCS Controller | Software | Critical Path | 2020-08-05 | 10 | 2020-10-14 | 4 | 2020-11-11 | 2 | 2020-11-25
| Comms Controller | Software | Critical Path | 2020-08-05 | 10 | 2020-10-14 | 4 | 2020-11-11 | 2 | 2020-11-25
| IFJR | Software | Critical Path | 2020-08-05 | 10 | 2020-10-14 | 4 | 2020-11-11 | 2 | 2020-11-25
| PMIC - EPS Controller | Software | Critical Path | 2020-08-05 | 10 | 2020-10-14 | 4 | 2020-11-11 | 2 | 2020-11-25
Important Dates
Name |  | Description | [7 empty] | Date
Radio Licensing Forms |  | All RF regulatory documents completed and being processed by regulatory bodies (FCC) | [7 empty] | 2020-03-01
Battery Qualification |  | Testing the batteries per the testing plan | [7 empty] | 2020-03-08
Flight Unit Integration |  | All flight ready hardware assembled, wiring harnesses installed | [7 empty] | 2020-11-11
Vibration Test |  | Mechanical test to ensure launch surviability, only critical hardware fixes will be installed | [7 empty] | 2020-11-18
Software Integration |  | All flight ready software installed, only critical bug fixes will be installed | [7 empty] | 2020-11-25
Day in the Life Test |  | A duration test of the flight unit in simulated space environment | [7 empty] | 2020-12-16
Nanoracks Handover |  | Delivery to launch provider | [7 empty] | 2020-12-30

## Gantt Lines
| Today: 04-Jun-20 | 2020-08-05 | 44048 | 44076
2020-06-04 | 0
2020-06-04 | 1
Radio Licensing Forms
2020-03-01 | 0
2020-03-01 | 1
Battery Qualification
2020-03-08 | 0
2020-03-08 | 1
Flight Unit Integration
2020-11-11 | 0
2020-11-11 | 1
Vibration Test
2020-11-18 | 0
2020-11-18 | 1
Software Integration
2020-11-25 | 0
2020-11-25 | 1
Day in the Life Test
2020-12-16 | 0
2020-12-16 | 1
Nanoracks Handover
2020-12-30 | 0
2020-12-30 | 1