## Text
CougSat-1 |  |  |  | V1.1.3 |  |  |  |  | End: | 2019-12-11
Subsystem | Component | Type | Start | Design |  | Implement Part 1 |  | Implement Part 2 |  | Test
Self-contained system within the satellite | Subassembly of the subsystem | Primary discipline | Component commencing | Outlining, prototyping, planning, diagraming, etc. |  | Schematic, mCAD, front end, interfacing, etc. |  | Board layout, machining, backend, assembly, etc. |  | Functional, performance, validation, etc.
CougSat-1 | Engineering Model | Assembly | 2018-05-02 | 3 | 2018-05-23 | 45 | 2019-04-03 | 4 | 2019-05-01 | 12 | 2019-07-24
| Flight Unit | Assembly | 2019-05-01 | 7 | 2019-06-19 | 8 | 2019-08-14 | 8 | 2019-10-09 | 9 | 2019-12-11
EPS | Mainboard | Hardware | 2018-05-23 | 2 | 2018-06-06 | 8 | 2018-08-01 | 16 | 2018-11-21 | 4 | 2018-12-19
| Solar Panel | Hardware | 2018-08-01 | 2 | 2018-08-15 | 8 | 2018-10-10 | 8 | 2018-12-05 | 4 | 2019-01-02
| Backplane | Hardware | 2018-08-29 | 2 | 2018-09-12 | 3 | 2018-10-03 | 8 | 2018-11-28 | 4 | 2018-12-26
| PMIC | Software | 2018-10-24 | 3 | 2018-11-14 | 8 | 2019-01-09 | 4 | 2019-02-06 | 4 | 2019-03-06
Avionics | Mainboard | Hardware | 2018-10-31 | 3 | 2018-11-21 | 8 | 2019-01-16 | 7 | 2019-03-06 | 4 | 2019-04-03
| ADCS Controller | Software | 2018-09-26 | 10 | 2018-12-05 | 10 | 2019-02-13 | 14 | 2019-05-22 | 7 | 2019-07-10
| IFJR Controller | Software | 2018-11-14 | 4 | 2018-12-12 | 8 | 2019-02-06 | 9 | 2019-04-10 | 9 | 2019-06-12
| IHU | Software | 2018-09-26 | 10 | 2018-12-05 | 7 | 2019-01-23 | 5 | 2019-02-27 | 10 | 2019-05-08
Communications | Comms PCB | Hardware | 2018-08-29 | 7 | 2018-10-17 | 8 | 2018-12-12 | 8 | 2019-02-06 | 4 | 2019-03-06
| Comms Controller | Software | 2018-11-14 | 7 | 2019-01-02 | 6 | 2019-02-13 | 14 | 2019-05-22 | 7 | 2019-07-10
| +X Panel | Hardware | 2018-09-26 | 3 | 2018-10-17 | 4 | 2018-11-14 | 8 | 2019-01-09 | 4 | 2019-02-06
| -Z Panel | Hardware | 2018-10-31 | 1 | 2018-11-07 | 4 | 2018-12-05 | 8 | 2019-01-30 | 4 | 2019-02-27
| Ground Station | Hardware | 2018-08-29 | 8 | 2018-10-24 | 4 | 2018-11-21 | 7 | 2019-01-09 | 4 | 2019-02-06
| Ground Computer | Software | 2018-05-23 | 3 | 2018-06-13 | 26 | 2018-12-12 | 19 | 2019-04-24 | 7 | 2019-06-12
Payload | Camera PCB | Hardware | 2018-10-24 | 3 | 2018-11-14 | 4 | 2018-12-12 | 8 | 2019-02-06 | 4 | 2019-03-06
| Germination PCB | Hardware | 2018-10-24 | 3 | 2018-11-14 | 4 | 2018-12-12 | 8 | 2019-02-06 | 4 | 2019-03-06
Mechanical | Structure | Hardware | 2018-05-23 | 3 | 2018-06-13 | 22 | 2018-11-14 | 8 | 2019-01-09 | 4 | 2019-02-06
| Germination | Hardware | 2018-05-23 | 7 | 2018-07-11 | 17 | 2018-11-07 | 4 | 2018-12-05 | 4 | 2019-01-02
Milestones
Name |  | Description | [8 empty] | Date
EM Integration |  | Assembly of all subsystems and components. Requires: all hardware done | [8 empty] | 2019-04-03
EM Day in the Life Test |  | A duration test of the satellite in simulated space environment. Requires: all software done | [8 empty] | 2019-07-10
FU Integration |  | Assembly of all flight ready subsystems and components | [8 empty] | 2019-08-14
FU Day in the Life Test |  | A duration test of the flight unit in simulated space environment | [8 empty] | 2019-10-09
FRR |  | Review of the flight unit to determine its readiness to fly | [8 empty] | 2019-10-30
MRR |  | Review of the mission to determine its readiness to execute | [8 empty] | 2019-11-20
ILC |  | Initial launch capabilities | [8 empty] | 2019-12-11
Formulas:
Date = [Date, row above]+21

## Gantt Lines (hidden)
| Today: 09-Nov-18 | 2019-12-17 | 43816
2018-11-09 | 0
2018-11-09 | 1
EM Integration
2019-04-03 | 0
2019-04-03 | 1
EM Day in the Life Test
2019-07-10 | 0
2019-07-10 | 1
FU Integration
2019-08-14 | 0
2019-08-14 | 1
FU Day in the Life Test
2019-10-09 | 0
2019-10-09 | 1
FRR
2019-10-30 | 0
2019-10-30 | 1
MRR
2019-11-20 | 0
2019-11-20 | 1
ILC
2019-12-11 | 0
2019-12-11 | 1