## Text
CougSat-1 |  |  |  | V1.1.1 |  |  |  |  | End: | 2019-08-13
Subsystem | Component | Type | Start | Design |  | Implement Part 1 |  | Implement Part 2 |  | Test
Self-contained system within the satellite | Subassembly of the subsystem | Primary discipline | Component commencing | Outlining, prototyping, planning, diagraming, etc. |  | Schematic, mCAD, front end, interfacing, etc. |  | Board layout, machining, backend, assembly, etc. |  | Functional, performance, validation, etc.
CougSat-1 | Engineering Model | Assembly | 2018-05-01 | 3 | 2018-05-22 | 40 | 2019-02-26 | 2 | 2019-03-12 | 8 | 2019-05-07
| Flight Unit | Assembly | 2019-03-12 | 8 | 2019-05-07 | 4 | 2019-06-04 | 4 | 2019-07-02 | 6 | 2019-08-13
EPS | Mainboard | Hardware | 2018-05-22 | 2 | 2018-06-05 | 8 | 2018-07-31 | 11 | 2018-10-16 | 4 | 2018-11-13
| Solar Panel | Hardware | 2018-07-31 | 2 | 2018-08-14 | 8 | 2018-10-09 | 5 | 2018-11-13 | 3 | 2018-12-04
| Backplane | Hardware | 2018-08-28 | 2 | 2018-09-11 | 3 | 2018-10-02 | 3 | 2018-10-23 | 3 | 2018-11-13
| PMIC | Software | 2018-10-23 | 3 | 2018-11-13 | 8 | 2019-01-08 | 3 | 2019-01-29 | 3 | 2019-02-19
Avionics | Mainboard | Hardware | 2018-08-28 | 3 | 2018-09-18 | 8 | 2018-11-13 | 7 | 2019-01-01 | 3 | 2019-01-22
| ADCS Controller | Software | 2018-09-25 | 7 | 2018-11-13 | 7 | 2019-01-01 | 3 | 2019-01-22 | 7 | 2019-03-12
| IFJR Controller | Software | 2018-11-13 | 3 | 2018-12-04 | 7 | 2019-01-22 | 3 | 2019-02-12 | 7 | 2019-04-02
| IHU | Software | 2018-09-25 | 3 | 2018-10-16 | 11 | 2019-01-01 | 3 | 2019-01-22 | 7 | 2019-03-12
Communications | Comms PCB | Hardware | 2018-08-28 | 7 | 2018-10-16 | 8 | 2018-12-11 | 8 | 2019-02-05 | 3 | 2019-02-26
| Comms Controller | Software | 2018-11-13 | 7 | 2019-01-01 | 3 | 2019-01-22 | 6 | 2019-03-05 | 7 | 2019-04-23
| +X Panel | Hardware | 2018-09-25 | 3 | 2018-10-16 | 2 | 2018-10-30 | 2 | 2018-11-13 | 3 | 2018-12-04
| Ground Station | Hardware | 2018-08-28 | 8 | 2018-10-23 | 2 | 2018-11-06 | 2 | 2018-11-20 | 3 | 2018-12-11
| Ground Computer | Software | 2018-05-22 | 3 | 2018-06-12 | 22 | 2018-11-13 | 16 | 2019-03-05 | 7 | 2019-04-23
Payload | Camera PCB | Hardware | 2018-10-23 | 3 | 2018-11-13 | 4 | 2018-12-11 | 4 | 2019-01-08 | 3 | 2019-01-29
| Germination PCB | Hardware | 2018-10-23 | 3 | 2018-11-13 | 4 | 2018-12-11 | 4 | 2019-01-08 | 3 | 2019-01-29
Mechanical | Structure | Hardware | 2018-05-22 | 3 | 2018-06-12 | 14 | 2018-09-18 | 7 | 2018-11-06 | 3 | 2018-11-27
| Germination | Hardware | 2018-05-22 | 7 | 2018-07-10 | 11 | 2018-09-25 | 7 | 2018-11-13 | 8 | 2019-01-08
Milestones
Name |  | Description | [8 empty] | Date
EM Integration |  | Assembly of all subsystems and components. Requires: all hardware done | [8 empty] | 2019-02-26
EM Day in the Life Test |  | A duration test of the satellite in simulated space environment. Requires: all software done | [8 empty] | 2019-04-23
FU Integration |  | Assembly of all flight ready subsystems and components | [8 empty] | 2019-06-04
FU Day in the Life Test |  | A duration test of the flight unit in simulated space environment | [8 empty] | 2019-07-02
FRR |  | Review of the flight unit to determine its readiness to fly | [8 empty] | 2019-07-16
MRR |  | Review of the mission to determine its readiness to execute | [8 empty] | 2019-07-30
ILC |  | Initial launch capabilities | [8 empty] | 2019-08-13
Formulas:
Date = [Date, row above]+14

## Gantt Lines (hidden)
| Today: 28-Oct-18 | 2019-12-17 | 43816
2018-10-28 | 0
2018-10-28 | 1
EM Integration
2019-02-26 | 0
2019-02-26 | 1
EM Day in the Life Test
2019-04-23 | 0
2019-04-23 | 1
FU Integration
2019-06-04 | 0
2019-06-04 | 1
FU Day in the Life Test
2019-07-02 | 0
2019-07-02 | 1
FRR
2019-07-16 | 0
2019-07-16 | 1
MRR
2019-07-30 | 0
2019-07-30 | 1
ILC
2019-08-13 | 0
2019-08-13 | 1